## BugsEnhancements Tracker
Sl No | Task | Type | Priority | Number of days | Comments | Date added | Status | Comments
1 | Vendor Login | Vendor regitration can have multiple child logins with parent data to be mapped once he registered with the parent PAN number | 3 | Medium change | 1 Day | 2022-11-10 | Testing
2 | Vendor Login | Vendor edit to add more type of work and integrate with all process of current integration |  | Major Change | 2 Days |  | Pending
3 | Vendor Login | Forgot passwrod to be given in the main login screen - Phase 1 |  |  | NA |  | Completed
4 | Vendor Login | Email triggers subject, body & footer to be shared by godrej and we will send the trigger points - Phase 1 |  |  | NA |  | Completed
5 | Vendor Login | From to be : Godrej Properties Contracts & Procurement - Phase 1 |  | Minor | NA |  | Completed
6 | Vendor Login | For entire site Add the assitance number of vendorglobe - (For website assistance contact : email ¦ number) - Phase 1 | 1 | Minor | 0.5 Day | Check with Sanmitha for the details | Completed | Live
7 | Vendor Login | Vendor not able to register on Portal |  | To be checked | 1 day |  | Completed
10 | Dashboard | "E mail Trigger Notification" - Mail triger to concern |  | Minor | 0.5 Day |  | Pending from GPL | Whatever templates were given are integrated
11 | Dashboard | Awarded data FY(22-23) should be a calendar which changes the data of NFA and RFQ related data. - Phase 2 |  | To be checked with NFA |  |  | Not to be taken
12 | Dashboard | IOM instead of NFA- Phase 2 |  |  | Ignore | Comes in NFA | Not to be taken
8 | Dashboard | Project Mapping under Rapid Configuration head:- |  |  | NA |  | Completed
9 | Dashboard | Additional points added for changes to be done in Portal on mail shared by VG team |  | Minor | 0.5 Day |  | Completed
10 | Dashboard | No. of vendor Empanelled to be reflected on Dashboard basis on PAN no. counts | 5 | Minor | 0.5 Day |  | Completed
11 | Dashboard | Reports | 27 | Major | In process ¦ 1 day |  | Pending
12 | Dashboard | Highlighting new works on the dashboard |  | Medium | In Process ¦ 1 day |  | Pending
13 | Dashboard | Bidder list to be there in higher dashboard, which has the collation of all the shortlisted vendors. | 6 | Medium change | 0.5 Day |  | Completed
14 | Dashboard | Filtration according to PAN CARDS registered in the registration table of the particular zone. | 7 | Medium change | 0.5 Day | 2022-11-10 | Pending
15 | Dashboard | Quick links at Dashboard | 4 |  |  |  | Completed
16 | Project Mapping | Edit project should have Not Applicable for PD and PM - Phase 1 |  | Minor | NA |  | Completed
17 | Project Mapping | · User can edit text for Project Name. |  |  | NA |  | Completed
18 | Project Mapping | · User cannot edit Purchase organisation code. |  |  | NA |  | Completed
19 | Project Mapping | 1 Project multiple PCM to be assigned |  |  | NA |  | Completed
25 | Project Mapping | Zonal Spoc - (According to the privilege of rapid) - |  | Major | Ignore | To be taken once we have nfa and rfq data | Not to be taken
20 | Project Mapping | Multi user selection from PD, PM and PCM throughout the system |  | Medium Change | This is already committed and in progress and will be delivered in a day |  | Completed
27 | IOM module | IOM to have same filter and table as vendor logs - Phase 2 |  |  | Ignore | Comes in NFA | Not to be taken
21 | Vendor Log | Some user's are not able to report Vendor log as add option is not visible |  | Minor | NA | This is based on user role. Could you kindly give the user example so that, we can check the role and update the privilege if needed | Completed
22 | Vendor Log | Vendor logs to have pan India option in the dashboard |  |  | NA |  | Completed
23 | Vendor Log | Vendor logs design to be checked with table header with color change | 8 | Minor | 0.5 Day |  | Completed
24 | Vendor Log | Vendor logs should have a date filter with a date range | 9 | Medium | 0.5 Day |  | Completed
25 | Vendor Log | Vendor logs to have pan India option in the dashboard and have Date filter and Date range for filtering | 10 | Minor Change | 0.5 day |  | Completed
26 | Vendor Log | Vendor logs design to be updated with table header with color change and better presentation for all user types and all places | 11 | Minor Change | 0.5 day for both point 39 and 40 |  | Completed
27 | Vendor Log | Vendor logs filters to be added by zone, project, vendor and current status | 12 | Medium change | 1 Day | 2022-11-10 | Completed
28 | vendor Database | Post selection of package as Core & shell, FB score of other packages is also seen | 28 | Minor | 1 day |  | Completed
29 | vendor Database | For the existing vendor with FB score, PQ score is also reflecting | 29 | Medium | 1 day | Could you please share an example so that, we can check if its a case scenario or a flow issue | Completed
38 | vendor Database | For FB score of 77, system is reflecting categorisation as very small | 30 | Minor | 0.5 Day | Could you please give the scrore ranges of financial categorization for feedbacks similar to PQ's | Pending from GPL | Please share the financial categorization scores for FB score thresholds
30 | Feedback | Feedback list to have Project name with purchase organization | 15 | Medium | 0.5 Day |  | Completed
31 | Feedback | PO city to be removed from feedback list (Everywhere) |  |  | NA |  | Completed
32 | Feedback | The main dashboard transferred count to be there along with pending | 22 | Medium | 1 day |  | Pending
33 | Feedback | Replicate the transfer facility similar for feedback along the lines of PQ (Mostly for RO C&P Head ¦RO C&P Team) and introduce the tracking for the same and update the corresponding Dashboards | 17 | Medium Change | 1 Day |  | Pending
34 | Feedback | Feedback list to have Project name with purchase organization | 18 | Very Minor | Ignore-able |  | Completed
35 | Feedback | PO city to be removed from feedback list (Everywhere) | 19 | Minor Change | Ignore-able |  | Completed
36 | Feedback | Feedback form completely re-structure for multiple form filling at a same time with table formation instead of new page redirection |  | Major Change | 3 Days |  | Pending
37 | Feedback | Feedback filter dashboard based on PAN selection - Will have zone wise/Project wise and score wise filtering with separate filter page and 1 entry per vendor | 21 | Medium change | This will be taken along with the point 43 |  | Pending
38 | Feedback | Selection of Feedback form should be mapped to PM ¦ PCM ¦ PD from the project mapping. | 16 | Medium change | 1 Day |  | Completed
39 | Feedback | · Single vendor feedback is coming multiple times. | 23 | Medium | 1 Day |  | Pending
40 | Feedback | · Feedback date is missing | 24 | Minor | 0.5 Day |  | Pending
41 | Feedback | · No dropdown to understand for which zone project score is mentioned. | 25 | Medium | 0.5 Day |  | Pending
42 | General | Highlighting the new works under the dashboard |  | Minor change | 0.5 day for point this and point 5 |  | Pending
43 | General | # to SL NO in all places - (Global) | 26 | Minor change | This will be taken along with the point 51 | 2022-11-10 | Completed
56 | Dashboard | In Dashboard of GPL vendor data, post selecting specific package, system display data of vendor for selected package alongwith data for other package registered by vendor. Ex - For the selection of "MEP Electrical" package, system display vendor details of " M/s Sai Balaji Infra which is registered as Electrical & also display data of other pacakge as Firefighting / HVAC / Plumbing etc. |  |  |  |  | Duplicate of point 36
44 | General | Add Package list (Finishing - Tiles) under vendor category & everywhere under Procurement Package heads. | 2 |  |  |  | Completed
58 | Vendor Login | Autosave of Vendor details on Portal such as Client / Project Name/etc. |  |  |  |  | Pending from GPL | Please elaborate on the point
45 | General | Token session error | 2 |  |  |  | Testing
46 | Dashboard | Auto generated mail received that vendor has initiated registation but not seen in stage 1 |  |  |  |  | Completed
47 | Vendor Login | Under stage 2 registration, All Financial Values such as turnover of vendor to be restricted upto 6 digit |  | Major |  |  | Completed
48 | Vendor Login | No attachment are vissible on Vendor registartion portal |  |  |  |  | Completed
49 | Dashboard | Cross buyer privilege for master user at present to be mapped to binit sirs credentials & also to Preeti and Piyush Jain
50 | Dashboard | Vendor Name is reflecting repetatively (ex - PG Interiors_PZ) |  |  |  |  | Completed | because of multple stage one regitsrations, it wont happen for new vendors as we have considered PAN validation in stage one regstration
65 | Dashboard | Autogenerated mail received for stage 1 acceptance but not able to view vendor name in portal (SZ) |  |  |  |  | Pending from GPL | Please share the mail format
51 | Vendor Login | Sunshine Tiles (MZ) : error - not able to submit at stage 2 (not able to autosave & Labour welfare fund is applicable but document not able to upload) |  |  | Stage two form draft to be taken |  | Completed | Explained on mail
52 | Vendor Login | Urbanac (SZ) : error - not able to submit at stage 2 |  |  |  |  | Completed | Explained on mail
53 | Vendor Login | Shapoorji (MZ) : Labour welfare & PT - NA but after filling undertaking form, Form is not getting saved |  |  |  |  | Completed | Explained on mail
54 | Vendor Login | Imperial Buildtech (SZ) : post completion of stage 1 error shown as - "vendor not found" |  |  |  |  | Completed
55 | Vendor Login | Vendor's - PQ score is not reflecting:- |  |  |  |  | Completed
56 | Vendor Login | Synergy, Multistorey (PZ) |  |  | Vendor is in stage one |  | Completed
57 | Vendor Login | Vardhusa (MZ) |  |  | Vendor is in stage one |  | Completed
58 | Vendor Login | Artistic Design works (PZ) : PAN no. is not reflecting at stage 2 & thus PQ is not reflecting |  |  | Vendor is in stage one |  | Completed
59 | Vendor Login | Ftechsolution(NZ) - Vendor was rejected at stage 1 due to wrong selection of category. Vendor re-registered but not showing in SPOC portal & vendor gets error - "Vendor rejected" at the time of login |  |  |  |  | Completed
60 | Vendor Log | In vendor log - "Issue Description" tab width is very less - Redesign page to view logs |  |  |  |  | Completed
61 | Vendor Log | Pain to GPL/Contractor - to be mandatory field |  |  |  |  | Completed
62 | Vendor Log | Vendor log - We should be able to download report in excel |  |  |  |  | Completed
63 | Dashboard | M/s Escon Elevators submitted stage 1 form but not seen in SPOC portal (MZ) to approve |  |  |  |  | Completed | Explained on mail
64 | Vendor Log | Status update by the user for open log is not visible to HO users (only date of Issue reported gets highlighted) |  |  |  |  | Pending
65 | Vendor Registration | Once stage_01 submitted to Vendor then Zonal spoc shall only PCM / ZOnal C&P |  |  |  |  | Not to be taken | This as explained, only to dedicated used this access is provided
66 | General | User shall be able to find out the vendor from PAN Card |  |  |  |  | Need Explaination | Can you please explain where this has to be given
67 | Vendor Registration | In stage _02 form declaration either of date to be delete |  |  |  |  | Not to be taken | As discussed, anything with regards to modification of forms won't be taken at this point
68 | Vendor Registration | Under stage 2--> step 2 ~ Experience with Similar Work (In last 5 years)* Upload experience to be changed to upload documents Under stage 2--> step 2 ~ REGISTERED WITH GOVERNEMENT DEPARTMENTS / PSUs / MAJOR DEVELOPERS : * Upload govt dept to be changed to upload Work order Under stage 2--> step 2 ~ Timely Completion Certification/ from Customers in last 5 years : * Target completion to be changed to completion date |  |  |  |  | Completed
69 | Vendor Registration | Under stage 2--> step 3 All the figures to be restricted to 6 digits such as total assets, current assets, total liabilities, current liailities, Turnover, Profits before Taxes, Profits after Taxes Profit & PAT should not exceed the turnover. |  |  |  |  | Completed | Not Completed
70 | Vendor Registration | Under stage 2--> step 2 ~ Experience with Similar Work (In last 5 years)* Details filled by vendor is not currently visible incase vendor dosent upload documents |  |  |  |  | Completed
71 | Vendor Registration | Under stage 2--> step 2 ~ REGISTERED WITH GOVERNEMENT DEPARTMENTS / PSUs / MAJOR DEVELOPERS : * Details filled by vendor is not currently visible incase vendor dosent upload documents |  |  |  |  | Completed
72 | Vendor Registration | Under stage 2--> step 2 ~ Timely Completion Certification/ from Customers in last 5 years : * Details filled by vendor is not currently visible incase vendor dosent upload documents |  |  |  |  | Completed
73 | Dash Board of Zonal SPOC | Under Dashboard--> Vendor Management--> Asiigned Task Under transfer colum:- Name of person is not visible to whom the form is transferred. Even after transfer the Zspoc, the transfer function is enabled. |  |  |  |  | Completed
74 | Dash Board of Zonal SPOC | Transfer function not working properly. Under Dashboard--> Vendor Management--> Assigned Task |  |  |  |  | Completed
75 | EOI | EOI bugs For example: EOI sent under Godrej Retreat / Contracts / Civil - Core & Shell/EOI not visible in PCM/User dashboard Contractor name to whom EOI is sent is not visible |  |  |  |  | Completed
76 | EOI | Godrej Retreat / Contracts / Civil - Core & Shell/EOI/ADD NEW/STEP 2 Entire vendor/contractor registered under that package category is not visible Vendor registered under core & shell category for NCR as primary location & checked for South in Interested Zones (Other than Primary location) then vendor name in selection of contractor in South zone EOI is not visible Contractor having feedbackscores is also not visible. |  |  |  |  | Completed
77 | EOI_Vendor Dash Board | Under vendor Dashboard--> EOI--> Bid Capacity--> Step 1 Financial years PAT cannot exceed Turn Over All the figures to be restricted to 6 digits |  |  |  |  | Completed
78 | EOI_Vendor Dash Board | Under vendor Dashboard--> EOI--> Bid Capacity--> Step 2 Expected Cummlative Billed amount in Cr by January 1970 (Expected completion date as per PCM input) to be rectified to Expected completion date to be rectified |  |  |  |  | Completed
79 | EOI_Vendor Dash Board | Under vendor Dashboard--> EOI--> Bid Capacity--> Step 2 Award date cannot be of before DOI |  |  |  |  | In Progress
80 | Mapping | Regional c&P ¦ Construction head ¦ operation head ¦ Regional head ¦ HO and COO to be rectified |  |  |  |  | Completed
81 | Projects listing in zonal dash | Zonal dashbaord dropdown |  |  |  |  | Completed
82 | Dashboard | Rename Approval time of the bidder to (Approval of bidder list) - NFA will come and sit here |  |  |  |  | Pending
83 | Vendor management | Only PCM / ZOnal C&P - Trnasfer |  |  |  |  | Completed
84 | Stage Two - Contractor | Remove date in epc and others in stage 2 | not Done |  |  |  | Completed
85 | Stage Two - Contractor | experience in similar work in last 5 years : Completion date to be changed to target completion date ¦ Upload experience to be changed to upload documents ¦ |  |  |  |  | Completed
86 | Stage Two - Contractor | Registered with Govt dept - Remove total billed value, start date and target completion ¦ Upload govt dept to be changed to upload Work order |  |  |  |  | Completed
87 | Stage Two - Contractor | Timely - Remove total billed value, start date and target completion |  |  |  |  | Completed
88 | Stage Two - Contractor | taxes before and after should not exceed turnover |  |  |  |  | Completed
89 | Stage Two - Contractor | Turnover to be restricted to 6 digits |  |  |  |  | Completed
90 | Stage Two - Contractor | Without uploads the table data to be retained |  |  |  |  | Completed
91 | Stage Two - Contractor | At stage one and stage two acceptance to have transfer ability |  |  |  |  | Completed
92 | Stage Two - Contractor | Transfer functionality entirely to be chacked |  |  |  |  | Completed
| Stage Two - Contractor | Stage_02_Step _06 Name of Vendor should come automatically
93 | Vendor management | SVR report - Name to be there |  |  |  |  | In Progress
94 | EOI | Feedabck vendors are not there in the EOI selection |  |  |  |  | Completed
95 | EOI | PAT cannot exceeef Tur over in (Vendor EOI Accept) |  |  |  |  | Completed
96 | EOI | Expected completion date to be removed in step 2(Vendor EOI Accept) |  |  |  |  | Completed
97 | Shortlisting | Award date should not be before DOI the DOI |  |  |  |  | Completed
98 | Shortlisting | Regional c&P ¦ Construction head ¦ operation head ¦ Regional head ¦ HO and COO to be rectified |  |  |  |  | Completed
99 | Shortlisting | Bid capacity to be checked |  |  |  |  | Completed
100 | Shortlisting | Financial to be decided as per the DOI of the company |  |  |  |  | Completed
101 | GPL Data Filter | Vendor management to be checked for GPL Vendor data |  |  |  |  | In Progress
102 | All Places | Dealer dropdown type work to be same vendor |  |  |  |  | Completed
103 | Stage Two - Dealer | Dealer stage 2 to be incorporated |  |  |  |  | Phase 2
104 | All Places | basic rated and free issues to be added (To be shared by piyush) |  |  |  |  | Pending From Godrej
105 | EOI And Shortlisting | Changes suggested for Contracts should be replicated for Procurement |  |  |  |  | In Progress
106 | EOI | Add EOI step-2 add sort on columns |  |  |  |  | Completed
107 | EOI | Total BUA - In million square foot: * (6 digits) |  |  |  |  | Completed
108 | EOI | Basic rates and Free issues to be mapped same for General category (As vendors linked to General category), same in https://cnp.gplapps.com/Staging/buyer/vendor/shortlistApproval/29 |  |  |  |  | Completed
109 | Shortlisting | If the network goes down - EOI is auto rejecting the bid capacity - Screenshot (20) taken for reference |  |  |  |  | Completed
110 | Shortlisting | List all the selected vendors in the status column to know the status of EOI |  |  |  |  | Completed
111 | Shortlisting | Error in vendors listing - refer Screenshot (21) - Bidding capacity and bidder category got interchanged |  |  |  |  | Completed
112 | Shortlisting | Error in vendors listing - refer Screenshot (22) |  |  |  |  | Completed
113 | Shortlisting | Selection of vendors to be there while sending for approval in shortlisting |  |  |  |  | Completed
114 | Shortlisting | Logic to be explained to Piyush regarding - Front Idling : Yes (As We are targeting the closure of the package by 15th June'22 i.e 30 days instead of 90 Days) |  |  |  |  | Completed
115 | Shortlisting | Selection of vendors to be there while sending for approval in shortlisting - (Rejected vendors should not come under send for approval |  |  |  |  | Completed
116 | Shortlisting | Shortlisting notification to be there in Quick links in the dashboard and actions required to be removed |  |  |  |  | Completed
117 | EOI | Civil general users to come in add EoI vendors list for civil related and infrastructure. |  |  |  |  | Completed
118 | All Places | Infrastructure is common for all other 3 |  |  |  |  | Completed
119 | Shortlisting | PQ/Feedback score of particular type of work should be populated in vendor list (EOI and Shortlisting) |  |  |  |  | Completed
120 | EOI | EOI status is not shown once shortlisting is approved |  |  |  |  | Completed
121 | IoM_Contract | Form fileds order need to be changed under Packages | DONE |  |  |  | Completed
122 | IoM_Contract | If only one package total column should hide | DONE |  |  |  | Completed
123 | IoM_Contract | Major terms package name has to come automatically | DONE |  |  |  | Completed
124 | IoM_Contract | In the add/edit page - breadcrumb - package/project | DONE |  |  |  | Completed
125 | IoM_Contract | OH/CH names are not showing in the approvers dropdown |  |  |  |  | Completed
126 | IoM_Contract | If there is any basic rate in tender - No, then remove the date | done |  |  |  | completed
127 | IoM_Contract | Basic rate consideration date should not be <= today’s date | done |  |  |  | completed | Updated as Basic rate consideration date < today’s date
128 | IoM_Contract | Final Bid Scenario - PQ/ Feedback Score / Scores lesser than pq<50 and feedback<60 for feedback and pq should be red highlighted |  |  |  |  | Completed
| IoM_Contract | Instertion of POP_UP i.e. diiference between the Present rate & Base rate | done
| IoM_Contract | Popup or text message should come for anticipated _"Please enter difference of today's base rate vs tender base rate" | Done |  |  |  | Completed
129 | IoM_Contract | Major Terms and Conditions - Description / Package Name (Rename) / Rename package name to description | Done |  |  |  | Completed
130 | IoM_Contract | Remove package box in major terms and conditions. Put inside the box and ensure its greyed out | Done |  |  |  | Completed
131 | IoM_Contract | Select different levels of approvals - cross verify the mapping | Not Done |  |  |  | Completed
132 | IoM_Contract | Package name (Final Bid Scenario Auto Reflect) |  |  |  |  | Completed
133 | IoM_Contract | Total expected(Expected Savings w.r.t Budget incl.escalation) formula should be - (total finalized - total budget)*100/total budget. | Done |  |  |  | Completed
| IoM_Contract | IOM is not travelling to the approving authority for approval
134 | IoM_Procurement | Form fileds order need to be changed under Packages |  |  |  |  | Completed
135 | IoM_Procurement | If only one package total column should hide |  |  |  |  | Completed
136 | IoM_Procurement | Major terms package name has to come automatically |  |  |  |  | Completed
137 | IoM_Procurement | In the add/edit page - breadcrumb - package/project |  |  |  |  | Completed
138 | IoM_Procurement | OH/CH names are not showing in the dropdown |  |  |  |  | Completed
139 | IoM_Procurement | Need to add extra rows with the same functionality as it is in contract(eg.Basis of award Deviation from Approved Contracting Strategy) |  |  |  |  | Completed
140 | IoM_Procurement | Need to check the formula issue for Expected Savings w.r.t Budget incl.escalation: |  |  |  |  | Completed
141 | IoM_Procurement | How many Contractors Recommended? - instead of contractors 'vendors' has to give |  |  |  |  | Completed
142 | IoM_Procurement | Is HO approval is Yes - 9 levels should come in approvers |  |  |  |  | Completed
143 | IoM_Procurement | Procurement Type need to remove |  |  |  |  | Completed
145 |  | For PQ/Feedback score - if PQ score <50, it should highlight with red color. |  |  |  |  | Completed
146 | EOI | Some users are not listing in EoI. Ex., Akhil user for Core and Shell, Check the login |  |  |  |  | Pending
147 | Filter | Add package name along with the filter results. |  |  |  |  | Pending
148 | IoM_Procurement | Rights for creation of IoM as per excel |  |  |  |  | Pending
149 | FIlter Logics | If there is Civil Core & Shell, Civil core and shell + Civil General, If its Civil General, all Civil Data (Same logic for all other types) |  |  |  |  | Pending
150 | Dashboard | Complete Dashboard completion |  |  |  |  | Pending
151 | IoM | Quick links for approval |  |  |  |  | Pending
152 | IoM_Contract | HO & CP - Binit name not reflecting |  |  |  |  | In Progress
| IoM_Contract | Based on recommended vendor, bidders count should come automatically. - dropdown numbers - lower value should be diasabled. | Not done |  |  |  | Completed
| IoM_Contract_Dashboard | For all approvers , in quick links it should display the pending count in red color. |  |  |  |  | Completed | New | Need clarification for some roles
| IoM_Contract | By default page filter display pending. |  |  |  |  | Completed | New | After testing some issues. Need to fix
| IoM_Contract | arc - IOMC, for procurement - IOMP |  |  |  |  | Completed | New
| IoM_Contract | After submission of IOM, PCM user will get edit option for the approval matrix for changing the pending users. |  |  |  |  | Pending | New
| IoM_Contract | Under Contractor Appointment Dates - Contract Package - needs to change description. below text box not required. |  |  |  |  | Completed
| IoM_Contract | If approval is pending, view button should display as Approve IOM else View |  |  |  |  | Completed | New
| IoM_Contract | In the view page - all NFA should be changed to IOM | Not Done |  |  |  | Completed
| IoM_Contract | SMTP mail needs to integrate and templates also to be provided |  |  |  |  | Completed
| IoM_Contract | For HO C&P, C00, HO C&P Head, MD (first 4 Role in add user under buyer management) - Zone should be there. for all others notrquired in the listing.. |  |  |  |  | Completed | New
| IoM_Contract | Listing Page - reduce width for ENFA No.(ENFA no. should be change to EIOM No.) | Not Done |  |  |  | Completed
| IoM_Contract | Change the order in the listing (in below sequence): 1. Sl. No 2. EIOM No. 3. Project Name 4. Package name 5. Actions 6. Scope of Work 7. IOM Status | Done |  |  |  | Completed | New
| IoM_Contract | Filter order needs to change and after selecting Zone, projects under zone should come Type Zone Project Name status After selecting Zone, projects under zone should come | Not Done |  |  |  | Completed | New
| IoM_Contract | Esign Option not required in the listing. |  |  |  |  | Completed
| IoM_Contract | In View - if all approvers are approved, for all approvers will show print PDF button | NOT DONE |  |  |  | Completed | New
| IoM_Contract | create IOM - PCM, RO C&P, RO C&P head ,HO C&P have the option to ceate IOM |  |  |  |  | Completed | New | Need project id/Package id for creating IOM. For some roles it is directly going to listing page
| IoM_Contract | In the Type - All (Needs to done. ) |  |  |  |  | Pending |  | Already discussed with Vinu about the difficulty
| IoM_Contract | In Award efficiency Start date of Bidder List approval - remove the validation |  |  |  |  | Completed
| IoM_Contract | In Award efficiency No of Days formula not working properly |  |  |  |  | Completed
| IoM_Contract | Formula should be triggered at any date box |  |  |  |  | Completed
| IoM_Procurement | Listing Page - reduce width for ENFA No.(ENFA no. should be change to EIOM No.) |  |  |  |  | Completed
| IoM_Procurement | For HO C&P, C00, HO C&P Head, MD (first 4 Role in add user under buyer management) - Zone should be there. for all others notrquired in the listing.. |  |  |  |  | Completed | New
| IoM_Procurement | Change the order in the listing (in below sequence): 1. Sl. No 2. EIOM No. 3. Project Name 4. Package name 5. Actions 6. Scope of Work 7. IOM Status |  |  |  |  | Completed
| IoM_Procurement | scope of work to be restricted for certain characters |  |  |  |  | Completed |  | In the backend it is restricted to 200 characters. So in the form also will be restriction upto 200
| IoM_Procurement | Proposed award value (excl tax) - Formula is not working |  |  |  |  | Completed
| IoM_Procurement | Rapid - MD role is missing | NOT DONE |  |  |  | Need to integrate extra conditions |  | Added the condition amt >=25 cr and other than L1
| IoM_Procurement | Bug in expected savings | NOT DONE |  |  |  | Completed
| IoM_Procurement | Qty box to be removed not required in Procurement other than Aluform / Steel rebar & cement | NOT DONE |  |  |  | Completed
| IoM_Procurement | No. of bidder list is not comming automatically | NOT DONE |  |  |  | Completed
| IoM_Procurement | Non mandatory field for PQ/FB score |  |  |  |  | Completed
| IoM_Procurement | Finalized Proposed Award value & recommended vendor to be Bold | NOT DONE |  |  |  | Completed
| IoM_Procurement | With save option - Major terms & condition gets erassed & we have to re-write |  |  |  |  | Completed
| IoM_Procurement | Instead of view - approve to be mentioned for approvers |  |  |  |  | Completed
| IoM_Procurement | In Award efficiency Start date of Bidder List approval - remove the validation | NOT DONE |  |  |  | Completed
| IoM_Procurement | In Award efficiency No of Days formula not working properly |  |  |  |  | Completed
| IoM_Procurement | Formula should be triggered at any date box |  |  |  |  | Completed
| IoM_Procurement | Under Approvers if the value is more than 25>= CR(In any case HO Approval) MD should come. |  |  |  |  | Completed
| IoM_Procurement | If in HO item is Yes, recemmender vendor other than L1 and amt >5 CR MD approval required |  |  |  |  | Completed
| IoM_Procurement | In view package column( package1, package2, package3) restrict to same width |  |  |  |  | completed
| IoM_Procurement | In the listing page width of EIOM No and scope work to be refixed. scope of work content can be come new line if it is lengthy. Actions to be visible without scroll. |  |  |  |  | Completed
| IoM_Procurement | In approve page change NFA to IOM |  |  |  |  | Completed
| IoM_Procurement | for procurement - arp needs to change as IOMP |  |  |  |  | Completed | New
| IoM_Procurement | after first level approval, OH user logins, filter type not showing. It is going to contracts currently |  |  |  |  | Completed | New
| Dashboard | Check the functionality for adding new package under basic rate | [5 empty] | New
| IoM_Procurement/Basic rate | In award efficiency "Receipt of Tender Document" change to "Receipt of CQS" and "Start date of Bidder List approval" change to "Start Date". This is applicable if we select package "Basic rate Approval" |  |  |  |  | Completed |  | In esign page need to do the change
| Dashboard | PCM Dashboard - Quick link for pending list of approval to be restricted to his assigned Projects only | [6 empty] | 1 hour
|  | Trend of last 1 year recent procurement for Material graph to be shown | [6 empty] | Half day
|  | General registered vendors to be filtered whenever specific package is selected | [6 empty] | 1 hour
| Dashboard | Vendor Database block has been changed in all dashboard with respective filters according to the privilege document | [6 empty] | Half day
| Dashboard | Average TAT - Got explanation from binit sir | [6 empty] | 30 mins
| Dashboard | Formula for the IOM related data in dashboard has been fixed as per binit sirs explanation |  |  |  |  | Completed
| Dashboard | Recent Procurement Rate - INR block has been fixed as per binit sirs explanation |  |  |  |  | Completed
| Dashboard | Quick links - Bidder list button has been added in all respective dashboards |  |  |  |  | Completed
| Dashboard | Removed shortlisting tab in all the dasboards |  |  |  |  | Completed
| All | Shorlisting nomenclature has been changed to Bidder list in all places |  |  |  |  | Completed and to be tested
| Bidder list/Shortlisting | Bidder list approval screen has been changed as per binit sirs explanation | [6 empty] | 2 hours
| Bidder list/Shortlisting | The pending works for the respective user from the dashboard has been implemented for both contracts and procurement EOI |  |  |  |  | Filters to be done |  | 2 hours
| Bidder list/Shortlisting | EOI type, Status, Zone and project filters has been provided in the bidder list approval screen for respective user as per privilege document | [6 empty] | 2 hours
| Bidder list/Shortlisting | Pending approvals has been added in the shortlisting approval screen |  |  |  |  | Completed
| Dashboard | Zonal data has been removed from the sidebar and added the in the dashboard screen as per privilege document |  |  |  |  | Completed
| Vendor Logs | Vendor logs addition privileges has been changed as per explanation |  |  |  |  | Completed
| Vendor Logs | Reason Attributable To and criticality fields has been added in the add screen |  |  |  |  | Completed
| Vendor Logs | List table has been changed with the color representation according to the criticality of the log |  |  |  |  | Completed
| Vendor Logs | Under change status criticality field has been added to the logs status |  |  |  |  | Completed
| Bidder list/Shortlisting | Add Manula bidder list tab has been provided as per privileges |  |  |  |  | Completed
| Dashboard | pending approvals count has been added in the dashboard with bidder list button - Both contracts and Procurement |  |  |  |  | To be tested |  | 1 hour
| Dashboard | Contracts - Inner pages | [6 empty] | 3 hours
| Dashboard | Procuremeent - Inner pages | [6 empty] | 3 hours
| Dashboard | Total C&P - Inner pages | [6 empty] | 3 hours
| Dashboard | Total number of Awards (FY 22-23) - Inner pages | [6 empty] | 3 hours
| Dashboard | Recent Procurement Rate - INR | [6 empty] | 3 hours
| Feedback - All | Feedback Management | [6 empty] | 3 hours
| Feedback - All | Feedback Management - Filter | [6 empty] | 3 hours
| Bidder list/Shortlisting | Manual BIdder list - contracts | [6 empty] | 3 hours
| Bidder list/Shortlisting | Manual BIdder list - Procurement | [6 empty] | 3 hours
| Bidder list/Shortlisting | Auto vendors bidder list - contracts | [6 empty] | 3 hours
| Bidder list/Shortlisting | Auto vendors bidder list - Procurement | [6 empty] | 3 hours
| Dashboard - All screens | Vendor Database | [6 empty] | 2 hours
| Dashboard - Vendor | Tender block | [6 empty] | 1 hour
| Dashboard - Vendor | Awarded contracts block | [6 empty] | 1 hour
| Dashboard - Vendor | Completed Contratcs block | [6 empty] | 1 hour
| Dashboard - Vendor | Quick actions bug fixes | [6 empty] | 1 hour
| Dashboard - Vendor | Logs to be captured eerywhere | [6 empty] | 2 Hours
| Dashboard | HO C&P users to get the snapshot off the IOM in the mail and dashboard | [6 empty] | 1 hour
| All | Financial year should start from 1st April - Global and end date is 31st of march | [6 empty] | 1 hour
| Dashboard | HO Operations to have different dashboard | [6 empty] | 1 hour
| Bidder list/Shortlisting | General registered vendors to be filtered whenever we select that related package | [6 empty] | 1 hour
| Dashboard | Quick linkl issue to be checked - Vendor dashboard | [6 empty] | 1 hour
| Bidder list/Shortlisting | Bread crums to be added in shortlistibg approval | [6 empty] | 30 mins
| Vendor Logs | In vendor issues in update or creation column on hover name of the last updated guy to be shown | [6 empty] | 30 mins
| All | Color code for PQ and Feedback scores to be done PQ is below 50 ¦ feddback is be;low 60 | [6 empty] | 30 mins
| Bidder list/Shortlisting | Manual / Dynamic color code bidder list | [6 empty] | 30 mins
| All | PM dashboard assigned feedback and svr to be fixed | [6 empty] | 2 hours
| Dashboard | Similar to Feedback reports and PQ reports for HO - Safety role | [6 empty] | 2 hours
| Dashboard | Height of the table entries to have margin bottom - All second click dashboard screens | [6 empty] | 30 mins
| Bidder list/Shortlisting | in bid capapcity Expected Cummlative Billed amount in Cr by cannot hgreater than work order amount | [6 empty] | 30mins
| Bidder list/Shortlisting | if completion lower than epqual to expected date it should be zero | [6 empty] | 30mins
| Bidder list/Shortlisting | Start and completion of the bidder lsit(Shortlisting) to be shown in the table | [6 empty] | 30mins
| Registration/Login | Vendors only can login with pan cards | [6 empty] | 1 hour
| All | In the cases of pre vendor having feedback score if pending feedback form filled by PM and select a category of contractor in feedback form the same category needs to be updfated in the profile of that vendor in additon to wwhta that vendor has selecte3d | [6 empty] | 2 hours
1 day
Testing entire module
Note on A1: Let me know when can you complete the test -Kashinath Gokarn
Note on H1114: Please let me know what kind of extra conditions need to be integrated. -Kashinath Gokarn

## Vendorglobe_Internal_Not_to_be_
Sl No | Task | Type | Number of working days | Comments | Date added
1 | "E mail Trigger Notification" - Mail triger to concern | Minor | 0.5 Day
2 | Edit project should have Not Applicable for PD and PM - Phase 1 | Minor | Completed
3 | Zonal Spoc - (According to the privilege of rapid) - Phase 1. Awarded data FY(22-23) should be a calendar which changes the data of NFA and RFQ related data. - Phase 2 | Major | Ignore | To be taken once we have nfa and rfq data
4 | For entire site Add the assitance number of vendorglobe - (For website assistance contact : email ¦ number) - Phase 1 | Minor | 0.5 Day | Check with Sanmitha for the details
5 | Vendors multiple profile to be brian storm - Phase 2 | Major
6 | IOM instead of NFA- Phase 2 |  | Its a part of NFA | Comes in NFA
7 | Vendor logs should have date filter with date range - Phase 2 | Medium | 0.5 Day
8 | IOM to have same filter and table as vendor logs - Phase 2 |  | Its a part of NFA | Comes in NFA
9 | From to be : Godrej Properties Contracts & Procurement - Phase 1 | Minor | Completed
10 | Email triggers subject, body & footer to be shared by godrej and we will send the trigger points - Phase 1 |  | Completed
11 | Forgot passwrod to be given in the main login screen - Phase 1 |  | Completed
12 | Project Mapping under Rapid Configuration head:- |  | Completed
13 | · User can edit text for Project Name. |  | Completed
14 | · User cannot edit Purchase organisation code. |  | Completed
15 | 1 Project multiple PCM to be assigned |  | Completed
16 | FB score
17 | · Single vendor feedback is coming multiple times. | Medium | 1 Day
18 | · Feedback date is missing | Minor | 0.5 Day
19 | · No dropdown to understand for which zone project score is mentioned. | Medium | 0.5 Day
20 | Additional points added for changes to be done in Portal on mail shared by VG team | Minor | 0.5 Day
21 | No. of vendor Empanelled to be reflected on Dashboard | Minor | 0.5 Day
22 | Some user's are not able to report Vendor log as add option is not visible | Minor | Completed | This is based on user role. Could you kindly give the user example so that, we can check the role and update the privilege if needed
23 | Post selection of package as Core & shell, FB score of other packages is also seen | Minor | 1 day
24 | For the existing vendor with FB score, PQ score is also reflecting | Medium | 1 day | Could you please share an example so that, we can check if its a case scenario or a flow issue
25 | For FB score of 77, system is reflecting categorisation as very small | Minor | 0.5 Day | Could you please give the scrore ranges of financial categorization for feedbacks similar to PQ's
26 | Vendor not able to register on Portal | To be checked | 1 day
27 | Vendor logs to have pan India option in the dashboard |  | Completed
28 | Vendor logs design to be checked with table header with color change | Minor | 0.5 Day
29 | Replicate the transfer facility similar to PQ for feedback for these two users (RO C&P Head ¦RO C&P Team) | Medium | 1 day
30 | Feedback list to have Project name with purchase organization | Medium | 0.5 Day
31 | PO city to be removed from feedback list (Everywhere) |  | Completed
32 | Feedback form restructure for multiple form filling (To be discussed with Vinu sir) | Major | 2 days | To be dicscussed with vinu
33 | The main dashboard transferred count to be there along with pending | Medium | 1 day
34 | Vendors multiple profiles to be brian storm | Major |  | To be dicscussed with vinu
35 | Vendor logs should have a date filter with a date range | Medium | 0.5 Day
36 | Reports | Major | In process ¦ 1 day
37 | Highlighting new works on the dashboard | Medium | In Process ¦ 1 day
38
39 | Vendor logs to have pan India option in the dashboard and have Date filter and Date range for filtering | Minor Change | 0.5 day
40 | Vendor logs design to be updated with table header with color change and better presentation for all user types and all places | Minor Change | 0.5 day for both point 39 and 40
41 | Replicate the transfer facility similar for feedback along the lines of PQ (Mostly for RO C&P Head ¦RO C&P Team) and introduce the tracking for the same and update the corresponding Dashboards | Medium Change | 1 Day
42 | Feedback list to have Project name with purchase organization | Very Minor | Ignore-able
43 | PO city to be removed from feedback list (Everywhere) | Minor Change | Ignore-able
44 | Feedback form completely re-structure for multiple form filling at a same time with table formation instead of new page redirection | Major Change | 3 Days
45 | In the main dashboard, transferred count to be there along with pending | Very minor | Ignore-able
46 | Vendor edit to add more type of work and integrate with all process of current integration | Major Change | 2 Days
47 | Reports | Medium Change | 1 Day
48 | Highlighting the new works under the dashboard | Minor change | 0.5 day for point this and point 5
49 | Multi user selection from PD, PM and PCM throughout the system | Medium Change | This is already committed and in progress and will be delivered in a day
50 | Feedback filter dashboard based on PAN selection - Will have zone wise/Project wise and score wise filtering with separate filter page and 1 entry per vendor | Medium change | This will be taken along with the point 43
51 | Bidder list to be there in higher dashboard, which has the collation of all the shortlisted vendors. | Medium change | 0.5 Day |  | 2022-11-10
52 | Filtration according to PAN CARDS registered in the registration table of the particular zone. | Medium change | 0.5 Day |  | 2022-11-10
53 | # to SL NO in all places - (Global) | Minor change | This will be taken along with the point 51 |  | 2022-11-10
54 | Selection of Feedback form should be mapped to PM ¦ PCM ¦ PD from the project mapping. | Medium change | 1 Day |  | 2022-11-10
55 | Vendor logs filters to be added by zone, project, vendor and current status | Medium change | 1 Day |  | 2022-11-10
56 | Bidder list to be there in higher dashboard, which has the collation of all the shortlisted vendors. | Medium change | 0.5 Day |  | 2022-11-10
57 | Vendor regitration can have multiple child logins with parent data to be mapped once he registered with the parent PAN number | Medium change | 1 Day |  | 2022-11-10
58 | Finishing - Tile to be added under vendor | Minor change
| Development |  | 30 working days
| Testing |  | 2 working days
| Total |  | 32 daysworking